CITY OF GREENFIELD

DECISION BRIEFING MEMORANDUM

Departmental Restructuring: Proposal A (Consolidate) vs. Proposal B (Targeted Fix)

| To: | Mayor and Members of the City Council |
| --- | --- |
| From: | Office of the City Manager - Management Analyst |
| Date: | October 19, 2026 |
| Subject: | Restructuring of five operating departments (Parks & Recreation, Sanitation, Transportation, Health Services, Fire Department; 596 authorized / 542 filled positions) - recommendation for the Council vote |
| Attachments: | Cost-Benefit Analysis Workbook (Greenfield_CostBenefit_Analysis.xlsx); Council Presentation (Greenfield_Council_Presentation.pptx) |

# 1. Purpose and Bottom Line

The Council will vote on two restructuring proposals for Greenfield's five operating departments. This memorandum presents the FY2024 operational baseline, a benchmark comparison against New York City's equivalent agencies (Mayor's Management Report and the NYS Comptroller's 2024 staffing-trends report), a cost-benefit model of each proposal, and a recommendation. All figures in this memo, the workbook, and the presentation are drawn from a single analysis of the city's FY2024 staffing, overtime, 311 service-request, and process-metrics data, benchmarked against the pinned NYC sources.

Recommendation: adopt the Hybrid option - implement Proposal B in full now (Phase 1), launch a gated and fully reversible Public-Works fleet-sharing pilot (Phase 2), and re-evaluate consolidation only if the pilot meets pre-agreed performance gates (Phase 3).

The recommendation scores highest on a transparent five-dimension rubric (Hybrid 3.6, Proposal B 3.4, Proposal A 3.2; weights: savings 30%, service-level improvement 30%, complexity 20%, risk 20%) and delivers the best risk-adjusted fiscal outcome: $1,580,027.75 cumulative three-year net savings versus $532,763.70 for Proposal B and $1,972,828.82 for Proposal A, while matching Proposal B's service-level gain (+8.3 percentage points on-time, 6 of 8 failing processes fixed) and avoiding Proposal A's negative first year ($-205,434.24).

# 2. Situation Overview: Staffing Health and Citizen Service Outcomes

## 2.1 Staffing health

Greenfield authorizes 596 positions across the five departments and fills 542, a citywide vacancy rate of 9.06% on an annual payroll of $28,389,900. Vacancy is unevenly distributed: Health Services (16.7%) and Transportation (14.9%) run at double-digit vacancy, while the Fire Department (3.5%) and Parks & Recreation (5.2%) are near full strength. Eight divisions - all four Transportation divisions and all four Health Services divisions - exceed the 12% vacancy trigger that Proposal B uses to activate centralized hiring, together accounting for 36 vacant positions.

## 2.2 Overtime cost structure

Departmental overtime totaled $4,354,518.25 in FY2024, 9.59% of regular hours. The cost is heavily concentrated: the Fire Department alone accounts for $2,085,312 (14.6% of its regular hours, above the 10% threshold in all 12 months) - roughly 48% of citywide OT spend. Sanitation sits just under the threshold at 9.8% (5 months above 10%), making it a watch-list case. Overtime per filled employee ranges from $4,127 (Parks) to $15,221 (Fire).

## 2.3 Citizen service outcomes

The FY2024 311 file contains 500 service requests: 437 closed with an average resolution time of 10.79 days (median 7.0, 90th percentile 30.4 days) and average satisfaction of 3.63/5. 63 requests remain open or in progress at year end - 58 older than 30 days and 47 older than 90 days, with the oldest request at 365 days. Of the 25 tracked business processes, 8 operate below the 65% on-time standard, including every Transportation field process measured.

Staffing health and service outcomes move together. Across the five departments, vacancy rate correlates with 311 resolution time at r = 0.67 and with resident satisfaction at r = -0.52. The two departments with the highest vacancy - Transportation and Health Services - also post the slowest 311 resolution (13.6 and 12.0 days) and account for 4 of the 8 sub-standard processes. This pattern is the analytical core of the decision: vacancies are not an HR statistic, they are visible in resident service outcomes, and they are being papered over with overtime.

| Department | Vacancy % | OT % of reg hrs | OT cost $ | 311 avg days | Satisfaction (1-5) | Worst on-time process | Worst on-time % | Procs <65% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Parks & Recreation | 5.2% | 6.05% | $453,960.00 | 12.5 | 3.55 | Tree Removal Request | 62.4% | 1 |
| Sanitation | 6.5% | 9.79% | $646,877.00 | 9.0 | 3.64 | Illegal Dumping Investigation | 54.2% | 2 |
| Transportation | 14.9% | 8.36% | $642,979.25 | 13.6 | 3.36 | Street Resurfacing Project | 48.3% | 3 |
| Health Services | 16.7% | 7.13% | $525,390.00 | 12.0 | 3.72 | Environmental Complaint Investigation | 64.1% | 1 |
| Fire Department | 3.5% | 14.57% | $2,085,312.00 | 3.8 | 4.23 | Plan Review (New Construction) | 59.6% | 1 |

Table 1. FY2024 department scorecard. Red-flag thresholds used throughout: vacancy >12%, OT >10% of regular hours, on-time <65%. Full detail: Workbook, "Baseline Metrics" tab.

# 3. NYC Benchmark Analysis

New York City is the pinned comparison because its five analog agencies (DPR, DSNY, DOT, DOHMH, FDNY) publish both service-performance indicators (Mayor's Management Report) and audited staffing/overtime analysis (NYS Comptroller, Report 2-2025). Three lessons transfer directly to Greenfield's decision.

## 3.1 Cost per employee: relative structure, not absolute dollars

| Department | NYC analog | NYC headcount (Jan-24) | NYC PS budget per FTE $ | Greenfield cost per employee $ | GF/NYC ratio |
| --- | --- | --- | --- | --- | --- |
| Parks & Recreation | DPR (Parks & Recreation) | 4,384 | 319,273 | 46,977 | 0.147 |
| Sanitation | DSNY (Sanitation) | 10,137 | 333,726 | 48,881 | 0.146 |
| Transportation | DOT (Transportation) | 5,117 | 355,865 | 54,288 | 0.153 |
| Health Services | DOHMH (Health & Mental Hygiene) | 5,355 | 346,254 | 67,006 | 0.194 |
| Fire Department | FDNY (Fire) | 17,016 | 379,774 | 80,954 | 0.213 |

Table 2. FY2024 expense budgets (NYC) vs. FY2024 payroll+OT per filled employee (Greenfield). NYC personal-services budgets include pension, fringe, and NYC wage scales, so the ratio is a relative sizing indicator only - but the ranking is instructive: Greenfield's cost structure mirrors NYC's, with Fire the most expensive per employee (21.3%% of the FDNY analog) and Parks the leanest.

## 3.2 Even a best-in-class system misses service targets

The MMR's latest cycle shows DOT closing 100% of potholes within 30 days against a 98% target (meets), DOHMH responding to birth-certificate requests in 2.6 days against a 3.0-day target (meets) - while FDNY misses both response-time targets (structural fires 4:22 vs. 4:08 target; life-threatening EMS 9:19 vs. 6:33). MMR time values are reported in minutes with decimal seconds. The lesson: service-level slippage in emergency-adjacent functions is a national pattern, so Greenfield's 59.6% on-time plan review and slow field processes should be treated as fixable operating problems, not evidence of structural failure.

## 3.3 The Comptroller's findings describe Greenfield's problem almost exactly

Vacancy is structural, not episodic - citywide vacancy was 5.1% in January 2024, down from the 8.4% December 2022 peak but far above the ~2% pre-pandemic norm; excluding schools and CUNY it is 4.6%. Greenfield's 9.06% sits at the same stress level. Greenfield is not an outlier; it is living through the same post-2020 workforce shock.

Overtime substitutes for vacancies - overtime reached $1,812,800,000 in FY2024 (1.8128B), up from $1,113,100,000 in FY2021, and rose from 7.0% to 10.8% of payroll. Overtime is substituting for vacant positions - precisely Greenfield's Fire Department pattern (14.57% OT, 3.5% vacancy).

Uniformed/frontline functions concentrate OT - FDNY fire extinguishment consumed 40.3% of departmental OT ($323,400,000), up from 28.9%; DSNY building cleaning OT share rose to 33.6%. Frontline response functions absorb vacancy pressure as overtime - arguing for OT-specific tools (caps, cross-training) rather than governance mergers.

Hiring machinery is slow - FDNY attrition runs 52% above pre-pandemic levels, and civil-service exam turnaround, while improving (318 to 219 to 169 days, FY21-FY24), still measures hiring in months. Any Greenfield plan that assumes rapid hiring must budget for a dedicated recruitment function - as Proposal B does.

The pattern is sector-specific - program-area vacancy rose from 6.7% to 10.0% in Transportation and 8.6% to 9.3% in Health, while Parks stayed low (1.3% to 1.8%) and DSNY/FDNY uniformed vacancies sit near zero. The same departments that are hard to staff nationally are the ones failing Greenfield's 12% trigger.

Benchmark conclusion: Greenfield's problem profile (double-digit vacancy in Transportation and Health, overtime-concentrated Fire, slow field processes) matches NYC's documented post-pandemic pattern. That supports interventions aimed at vacancies and overtime specifically - and cautions against organizational surgery whose benefits NYC's own data cannot confirm.

# 4. Proposal A - "Consolidate": Evaluation

Proposal A merges Health Services and Parks & Recreation into a Department of Community Wellness, and Transportation and Sanitation into a Department of Public Works; the Fire Department remains standalone. Headcount becomes three entities: Community Wellness 177 authorized / 166 filled (6.2% vacancy), Public Works 267 authorized / 249 filled (6.7% vacancy), Fire 142 authorized / 137 filled (3.5% vacancy).

## 4.1 Process bottlenecks addressed

The merger's service logic is strongest where field processes fail together: Public Works would own the four failing Transportation/Sanitation field processes (Street Resurfacing 48.3% on-time, Illegal Dumping 54.2%, Bulk Pickup 58.1%, Sidewalk Repair 61.7%) and could pool crews, routing, and dispatch. Community Wellness pairs Environmental Complaint Investigation (64.1%) with Tree Removal (62.4%) and Playground Inspection (78.2%), enabling a shared inspection workforce.

## 4.2 Overtime cost structure

Proposal A models OT savings of $355,906.25: a 20% reduction on Public Works' combined $1,289,856.25 base ($257,971.25) and 10% on Community Wellness' $979,350.00 base ($97,935.00). Critically, the Fire Department - the city's largest OT cost center at $2,085,312.00 - is excluded from the merger and its overtime is untouched.

## 4.3 Financial model

| Component | Basis | Annual value |
| --- | --- | --- |
| OT consolidation savings | 10% CW + 20% PW of FY2024 OT cost | $355,906.25 |
| Administrative elimination | 9 positions (2.0% of merged authorized) via attrition, $48,002 avg salary x 1.35 loaded | $583,225.28 |
| Shared fleet & procurement (OTPS) | Common maintenance bays, bulk fuel/parts contracts, pooled spares | $150,000 |
| Steady-state annual savings | Sum of above | $1,089,131.53 |
| One-time transition cost | MOU/labor relations $250K; HRIS/payroll integration $300K; fleet logistics $120K; transition team $80K | ($750,000) |
| Year 1 net (50% realization) | Transition year | $-205,434.24 |
| Year 2-3 net (100%) | Steady state | $1,089,131.53/yr |
| 3-year cumulative net |  | $1,972,828.82 |

Table 3. Proposal A fiscal model. Full assumptions: Workbook, "Proposal A Model" tab (A1-A8).

## 4.4 SLA risk, workforce feasibility, verdict

Modeled service gains average +6.2pp on-time across 8 targeted processes, with 5 reaching the 65% standard; cycle-time improvements are proportional (e.g., Street Resurfacing 45.2 to 39.0 days). But the model must be read against a 24-month implementation: dispatch consolidation, CBA renegotiation, and HRIS cutover all occur before savings appear. Workforce feasibility is the binding constraint: 24 FTEs are reallocated (9 admin positions eliminated strictly via attrition, 15 field FTEs flexibly deployed), and merger-scale labor agreements carry real delay risk. Verdict: Proposal A offers the largest steady-state savings but a negative first year, the highest complexity (4/5) and risk (4/5), leaves Fire overtime untouched, and its OT-savings premise (20% from merged routing) is the least-supported number in either proposal.

# 5. Proposal B - "Targeted Fix": Evaluation

Proposal B keeps all five departments and activates three interventions, each tied to an objective trigger.

| Intervention | Trigger | Triggered units | Design |
| --- | --- | --- | --- |
| Shared OT budgets / OT cap | Department OT >10% of regular hours | Fire Department (14.57%, 12 of 12 months). Sanitation (9.79%, 5 months) placed on watch list | Cap Fire OT at 13% of regular hours; joint budget review |
| Centralized hiring | Division vacancy >12% | 8 divisions (all 4 Transportation, all 4 Health Services); 36 vacancies | Central recruitment team + vacancy dashboard; 22 of 36 filled in Year 1 |
| Cross-training pools | Departments with shared surge processes | 3 pools, 45 members (Field Ops 24; Inspection & Public Health 12; Fleet & Facilities 9) | 40 hours initial training; annual refresh |

Table 4. Proposal B trigger map. Detail: Workbook, "Proposal B Model" tab.

## 5.1 Overtime cost structure

The OT cap removes 4,670 excess Fire overtime hours (FY2024 OT of 43,444 hours against a 13% cap of 38,773 hours on 298,260 regular hours), a 10.7% cut priced at the blended rate of $48.00/hour: $224,160.00 annually. Centralized hiring attacks the vacancy-driven share of OT (assumed 25%) in the two triggering departments: $178,539.08 in Year 1 (22 fills) rising to $292,092.31 once all 36 vacancies are filled.

## 5.2 Financial model

| Component | Basis | Value |
| --- | --- | --- |
| Fire OT cap savings | 4,670 hours x $48.00 blended rate | $224,160.00 |
| Vacancy-driven OT savings | 25% backfill share; Transportation + Health Services | $178,539.08 Y1; $292,092.31 Y2+ |
| Steady-state annual savings | Cap + fully realized vacancy savings | $516,252.31 |
| Program costs | Hiring team 3 FTE $234,900/yr; training refresh $15,000/yr; dashboard $40,000; initial cross-training $56,700 | ($249,900.00)/yr ongoing + ($96,700.00) one-time |
| Year 1 net | Cap effective Q2 (75%); phased hiring | $59.08 |
| Year 2-3 net | Steady state | $266,352.31/yr |
| 3-year cumulative net |  | $532,763.70 |

Table 5. Proposal B fiscal model. Year 1 is deliberately break-even: the city buys capability first, savings follow. Full assumptions: Workbook (B1-B9).

## 5.3 SLA improvement, workforce feasibility, verdict

Because the interventions land directly on the failing processes - centralized hiring on the vacancy-driven departments, cross-trained surge capacity on field processes - Proposal B projects the largest service gain: +8.3pp average on-time improvement with 6 of 8 processes reaching the 65% standard (including Plan Review 59.6% to 66.0% and Illegal Dumping 54.2% to 67.0%), and cycle-time cuts on every targeted process. Workforce feasibility is high: no mergers, no CBA renegotiation, 48 FTEs touched (45 cross-trained + 3 hiring team), 12-month timeline, complexity 2/5 and risk 2/5. Verdict: the best service and risk profile, but the lowest cumulative savings - it leaves the fleet and procurement duplication that motivates Proposal A unaddressed.

# 6. Comparative Assessment

| Dimension | Proposal A - Consolidate | Proposal B - Targeted Fix | Hybrid (recommended) |
| --- | --- | --- | --- |
| Annual cost savings (3-yr avg net) | $657,609.61 | $177,587.90 | $526,675.92 |
| FTEs reallocated | 24 | 48 | 60 |
| Projected SLA improvement | +6.2pp; 5 processes fixed | +8.3pp; 6 processes fixed | +8.3pp; 6 processes fixed |
| Complexity (1-5) | 4 | 2 | 3 |
| Risk (1-5) | 4 | 2 | 3 |
| Year-1 net | $-205,434.24 | $59.08 | $89,551.89 |
| 3-year cumulative net | $1,972,828.82 | $532,763.70 | $1,580,027.75 |
| Timeline (months) | 24 | 12 | 12 |
| Net recommendation score | 3.2 / 5 | 3.4 / 5 | 3.6 / 5 |

Table 6. Five-dimension comparison (shaded column = recommendation). Scores use the transparent rubric in the Workbook "Comparison Summary" tab: savings points on 3-year average annual net (>=900K=5, >=600K=4, >=400K=3, >=200K=2, >0=1), SLA points on average percentage-point gain (>=8=5, >=6=4, ...), complexity and risk inverted (6 - level), weighted 30/30/20/20.

# 7. Recommendation: A Phased Hybrid

Adopt Proposal B in full now; run a gated, reversible fleet-sharing pilot; decide on consolidation only if the gates are met.

Phase 1 (months 0-12): implement every Proposal B intervention - the Fire OT cap at 13% of regular hours, centralized hiring for the 8 triggered divisions (36 vacancies; 22 fills targeted in Year 1), and the three cross-training pools (45 members) - with the hiring team and vacancy dashboard stood up in Q1 and the OT cap effective in Q2. Year 1 nets $59.08 by design; steady-state net is $266,352.31/yr from Year 2.

Phase 2 (months 6-24): establish joint Fleet & Equipment Operations across Sanitation, Transportation, and Parks maintenance - shared maintenance bays, bulk fuel/parts contracting, pooled spare vehicles - without merging the departments. Captures $150,000 of fleet OTPS savings plus $128,986 (half of the modeled Public Works OT synergy) against a $50,000 pilot cost. Every element is reversible by MOU at 90 days notice.

Phase 3 (month 24+): only if the pilot passes pre-agreed gates - quarterly OT% and on-time% targets met for four consecutive quarters - should the Council re-open the consolidation question with the evidence Proposal A currently lacks.

The quantitative case for the Hybrid: it matches Proposal B's service gain (+8.3pp, 6 processes fixed) because it contains all of B; it recovers roughly two-thirds of Proposal A's steady-state savings ($745,238/yr vs. $1,089,132) while avoiding A's negative first year (Hybrid Year 1: +$89,551.89); its three-year cumulative net of $1,580,027.75 is 3.0x Proposal B's and 80% of Proposal A's - but Proposal A's figure assumes merger synergies materialize on schedule, which its own 4/5 complexity and risk ratings argue against. On risk-adjusted expected value the Hybrid dominates: its savings rest on interventions with direct data triggers, its only speculative element (the fleet pilot) is small, gated, and reversible.

What this recommendation deliberately does not do: no layoffs (attrition only), no change to the Fire Department (its vacancy and OT problems are addressed by B's tools, and NYC data shows frontline functions resist consolidation economics), and no merger during a 9.06%-vacancy hiring market.

# 8. Risks and Mitigations

| Risk | Likelihood/Impact | Mitigation |
| --- | --- | --- |
| Hiring market cannot deliver 22 fills in Year 1 (Comptroller: NYC exam turnaround 169-318 days) | Medium / High | Dedicated 3-FTE hiring team; contract recruiters for hard-to-fill titles; phased targets with quarterly reporting |
| OT cap shifts work to unfilled demand (slower response, not lower cost) | Medium / Medium | Cap paired with cross-training pools and monthly OT% monitoring; Sanitation watch-list review at mid-year |
| Fleet pilot drifts into de-facto merger, recreating Proposal A risks | Low / Medium | Reversible MOU with 90-day exit; quarterly gates; no transfer of personnel authority |
| Savings overstated (single-year 311 sample of 500 requests; blended OT rate; 25% backfill share) | Medium / Medium | Conservative haircut already applied to merger synergy (50%); re-baseline after FY2025 close; dashboard tracks actual vs. model |
| Council credibility: metrics drift after the vote | Low / High | Quarterly public scorecard on the four red-flag metrics (vacancy, OT%, on-time%, 311 resolution) |

# 9. Assumptions Register (consolidated)

Proposal A (A1-A8): OT reduction 10% CW / 20% PW on FY2024 OT cost bases; admin elimination 2.0% of merged authorized positions (9 FTE) via attrition only; fringe/load factor 1.35x salary; fleet OTPS savings $150,000/yr (planning estimate); one-time transition $750,000 as itemized; realization 50%/100%/100%; Fire unchanged; service projections assume merged dispatch/crew flexibility lifts on-time% as tabled.

Proposal B (B1-B9): OT cap 13% of regular hours, applied only to departments above the 10% trigger (Fire); excess hours priced at blended rate $48.00/hr; 25% of triggering departments' OT attributed to vacancy backfill; 60% of triggered vacancies filled in Year 1 (22 of 36), 100% by end of Year 2, savings scale with fills; hiring team 3 FTE at $58,000 x 1.35; cross-training 45 members x 40 hours x $31.50 loaded; dashboard $40,000 one-time; refresh $15,000/yr; Sanitation on watch list only; no boundary, CBA, or title changes.

Hybrid (H1-H3): captures A's fleet OTPS savings ($150,000) without governance change; captures 50% of modeled PW OT synergy ($128,986) via pooled routing only; pilot cost $50,000; fleet savings counted only from the pilot's effective quarter (50% in Year 1).

# 10. Next Steps and Decision Requested

| # | Action | Timing | Owner |
| --- | --- | --- | --- |
| 1 | Council adopts the Hybrid resolution (Phase 1: Proposal B interventions in full) | This session | Council / City Manager |
| 2 | Stand up centralized hiring team (3 FTE) and vacancy dashboard | Q1 | HR Director |
| 3 | Fire Department OT cap effective at 13% of regular hours; monthly OT% reporting begins | Q2 | Fire Chief / Budget Office |
| 4 | Cross-training pools launched (45 members; 40-hour curriculum) | Q2-Q3 | Department heads |
| 5 | Fleet-sharing pilot MOU executed with gates and 90-day reversal clause | Month 6 | City Manager / Fleet |
| 6 | First quarterly public scorecard (vacancy, OT%, on-time%, 311 resolution) | Q3 | Management Analyst |
| 7 | Gate review: consolidation re-evaluation only if four consecutive quarters pass | Month 24 | Council |

# Appendix A. Sources

[1] Greenfield_311_Service_Requests_FY2024.csv - 500 service requests, FY2024 (Jul 2023-Jun 2024).

[2] Greenfield_Dept_Staffing_Overtime_FY2024.xlsx - Staffing_Summary, Monthly_Overtime, Process_Metrics sheets.

[3] NYC_Expense_Budget_Selected.csv - NYC FY2023-FY2025 expense budgets, PS/OTPS split (FY2024 used).

[4] NYC_MMR_Selected_Agencies.csv - Mayor's Management Report indicators (NYC Open Data rbed-zzin snapshot), latest reported cycle.

[5] NYC_Staffing_Trends_2024.pdf - NYS Comptroller, Report 2-2025, "2024 Update on New York City Staffing Trends."

All computations reproducible from /work/analysis.py and /work/output/analysis_results.json.

# Appendix B. 311 Service Requests by Department and Category (FY2024)

| Department | Category | Requests | Avg resolution (days) | Satisfaction (1-5) | Open/in-progress |
| --- | --- | --- | --- | --- | --- |
| DHS | Food Safety | 15 | 10.6 | 3.88 | 1 |
| DHS | Mold/Air Quality | 6 | 15.4 | 3.33 | 1 |
| DHS | Noise Complaint | 19 | 11.1 | 3.73 | 4 |
| DHS | Restaurant Inspection Request | 13 | 18.7 | 2.57 | 2 |
| DHS | Rodent Sighting | 15 | 10.7 | 4.25 | 0 |
| DHS | Unsanitary Conditions | 2 | 4.0 | 3.5 | 0 |
| DHS | Water Quality Concern | 5 | 6.2 | 4.33 | 1 |
| DOT | Crosswalk Faded | 6 | 23.8 | 2.0 | 2 |
| DOT | Pothole | 36 | 14.9 | 3.33 | 4 |
| DOT | Road Debris | 9 | 10.7 | 3.5 | 0 |
| DOT | Sidewalk Damage | 20 | 11.5 | 3.23 | 3 |
| DOT | Street Sign Missing | 7 | 13.1 | 3.43 | 0 |
| DOT | Streetlight Outage | 31 | 13.3 | 3.62 | 3 |
| DOT | Traffic Signal Malfunction | 17 | 13.1 | 3.3 | 2 |
| DPR | Bench/Fountain Repair | 8 | 15.8 | 2.8 | 2 |
| DPR | Fallen Tree | 17 | 10.1 | 4.0 | 1 |
| DPR | Graffiti Removal | 16 | 12.7 | 3.12 | 5 |
| DPR | Overgrown Vegetation | 9 | 10.8 | 3.4 | 1 |
| DPR | Park Maintenance | 26 | 16.0 | 3.54 | 4 |
| DPR | Playground Equipment Damage | 19 | 11.3 | 3.77 | 1 |
| DPR | Trail Obstruction | 4 | 4.0 | 3.67 | 1 |
| DSNY | Bulk Item Pickup | 22 | 9.7 | 3.91 | 4 |
| DSNY | Illegal Dumping | 23 | 9.4 | 3.8 | 1 |
| DSNY | Litter on Street | 11 | 6.6 | 3.5 | 2 |
| DSNY | Missed Pickup | 43 | 11.0 | 3.36 | 3 |
| DSNY | Overflowing Bin | 17 | 10.7 | 4.0 | 2 |
| DSNY | Recycling Violation | 21 | 6.0 | 3.75 | 4 |
| DSNY | Street Sweeping Complaint | 11 | 3.6 | 3.62 | 2 |
| FDNY | Blocked Fire Exit | 2 | 2.5 | 5.0 | 0 |
| FDNY | Building Fire Safety Concern | 11 | 7.1 | 3.83 | 1 |
| FDNY | Carbon Monoxide Concern | 8 | 2.2 | 4.33 | 3 |
| FDNY | False Alarm Report | 3 | 1.0 | 4.0 | 1 |
| FDNY | Fire Hydrant | 18 | 1.6 | 4.18 | 2 |
| FDNY | Smoke Detector Request | 10 | 5.8 | 4.5 | 0 |